## Slide 1: BB Scheduler Update Week 9
Waukesha School District/Obsidian Solutions

## Slide 2: Agenda
GUI Status
Testing Servers Status
Business Logic Status
LTI API Status
Documentation Status
Next Steps
Wrap Up

## Slide 3: GUI Status
BB Scheduler
  Walk Through Prototype
  Started Testing ADMIN Mode
  Manage IC Courses
    New Logo
    Refactor Manage Sections to allow multi-tasks
    Remove Section – Disables Enrollments
    Added Messaging to Course Creation
    Added Confirm Pop-Ups in Manage Sections
  Manage BB Courses
    UI Table Done With Filter/Sort
    Added Actions
    Added Info Button
    Added Manage BB Course
    Discuss Manage Teachers
    Discuss Manage Students
    Discuss Add Section
  Manage Grades
    Discuss

## Slide 4: TESTING SERVERs STATUS
Testing Servers
  Staging Server - DONE
    Using Vendor Login
  Windows Server - ADMIN
    Need to Install Tomcat 10 - DONE
    Need HTTPS Access – Need Signed Certificates DONE
    Installed Version 0.0.3
      Need Public IP Address
      Need Port 80/443 … port Forwarding
      Need SMTP Server/config for Emails
      Need BB Production Server access for configuration
Notes: - DONE

## Slide 5: BUSINESS LOGIC STATUS
Sync Process
  Student/Staff Sync – DONE
  Enrollment Sync – DONE
  Group Sync – TESTING
Manage Teachers
  Get Teachers in BB Course … Allow Remove or Add??
Manage Students
  Get Students in BB Course … Allow Remove or Add??
Add Section in BB Course???
When we change Course Name and Description – Need in 2 areas

## Slide 6: LTI API Status
Implement LTI 1.1
  Endpoint Works – Using IMS Basic Utils Library
  Passing in Username as Custom Parameter
  Getting Return URL
  Added to System
  Launch as Separate Window or Modal?
  Adding Swagger REST API points
  Where will this be located?
    SYSTEM
    COURSE
    TOOL

## Slide 7: Course Create Flow
User Selects:
  Template (source course id)
  BB Course Name (prepopulated and editable)
  BB Course Description (Input From User)
  Add Teachers and Students
  User Clicks ”Add Course”
Process
  Create entry into SDWBlackboardSchedulerBBCourses .. Get KEY Value (bbCourseID)
  Add Key to BB Course ID
  Create Course in BB Learn from Template Chosen
  Update SDWBlackboardSchedulerBBCourses with new Course ID
  Update BB Course with Course Name and Course Description
  Add Enrollments from Sections
  Create entries into SDWBlackboardSchedulerSISCourseSections
  Create entries into SDWBlackboardSchedulerSISCoursePersons
  Groups for PreExisting Courses??

## Slide 8: User/ENROLLMENT SYNC
User Sync
  Built into Application – Spring Task – Run at specific Times
  Uses BB Data Integration Framework – Snapshot Files
  Build Person File (Student and Staff)
  Build Staff Secondary Role File
  Need Logic for Institution Roles
Enrollment Sync
  Use Entries SDWBlackboardSchedulerSISCourseSections
  Use Entries SDWBlackboardSchedulerSISCoursePersons
  Added Group Fields
  Create Enrollment File to BB Data Integration Framework
  BB Data Integration does not support Groups.
  Recent Database Sync has lots of errors …. BB Courses Not in Staging
  Adding Group Sync – Just Push

## Slide 9: Next STEPS
BB Scheduler
  Add Modify Sections
  Add Teacher and Students
  Discuss ”Manage Grades”
  Discuss “Admin” Role
BB Integration
  NONE
LTI API Implementation
  Test and verify on Windows Server
Windows Servers
  Test Login and Start Configuring
Continue UI Implementation
  Estimate 4 Weeks
Start Installation/Configuration Documents

## Slide 10: Wrap up
Estimate 4-6 Weeks left
Any Concerns or Requests?
Questions/Answers