## Slide 1: BB Scheduler Update Week 7
Waukesha School District/Obsidian Solutions

## Slide 2: Agenda
REST API Status
Infinite Campus DB Status
LTI API Status
GUI Status
Testing Servers Access
Next Steps
Wrap Up

## Slide 3: Rest API status
REST API Development
  Framework Started
  TERM Rest Endpoint
    Get all TERMS
  COPY COURSE Endpoint
    Done
  COURSE REST Endpoint
    Get Course Information
    Update Course Information
  MEMBERSHIP REST Endpoint
    Get all Enrollments for a User
    Create Enrollment
  GRADEBOOK Rest Endpoint
    Get all grades for a User
    Get Column Information
    Get Category Information
  USER Rest Endpoint
    Get All Users
    Get User Information
    Create/Update Users
  GROUP Rest Endpoint
    Create Group Set/Groups
    Add User to Group

## Slide 4: Infinite campus DB status
SQL Server Database
  JDBC URL Defined - DONE
  Need Port Opened for Development Server (Request Sent) - DONE
  Need SQL Calls used in version 1
    GetCalendars – Not Used
    GetCourses -DONE
    GetSections – DONE
    GetEnrollments – DONE
    GetMasterTemplates – DONE
    Insert/Update SDWBlackboardSchedulerBBCourses – DONE
    Insert/Update SDWBlackboardSchedulerSISCoursesSections- DONE
    Insert/Update SDWBlackboardSchedulerSISCoursesPersons- DONE
    Get Teachers – DONE
    Get Students - DONE

## Slide 5: LTI API Status
Implement LTI 1.1
  Endpoint Works – Using IMS Basic Utils Library
  Passing in Username as Custom Parameter
  Getting Return URL
  Added to System
  Launch as Separate Window or Modal?
  Adding Swagger REST API points
  Where will this be located?
    SYSTEM
    COURSE
    TOOL

## Slide 6: GUI Status
BB Scheduler
  Walk Through Prototype
  ICON too small to see
  Added Manage Sections (Review)
    Add Section to Existing BB Course
    Remove Section from BB Course
    Issues with Groups for Preexisting BB Courses
  Change Labels in the Course Create Sheet
  Added Green Highlight to Courses Selected
  Added Student Number to Student List
  Course Creation courses are now Always Available

## Slide 7: TESTING SERVERs ACCESS
Testing Servers
  Staging Server - Needed
    Using Vendor Login
  Windows Server - ADMIN
    Need to Install Tomcat 10 - DONE
    Need HTTPS Access – Need Signed Certificates DONE
    Email from Steve Received – Not Tested yet
Notes: - DONE

## Slide 8: Course Create Flow
User Selects:
  Template (source course id)
  BB Course Name (prepopulated and editable)
  BB Course Description (Input From User)
  Add Teachers and Students
  User Clicks ”Add Course”
Process
  Create entry into SDWBlackboardSchedulerBBCourses .. Get KEY Value (bbCourseID)
  Add Key to BB Course ID
  Create Course in BB Learn from Template Chosen
  Update SDWBlackboardSchedulerBBCourses with new Course ID
  Update BB Course with Course Name and Course Description
  Add Enrollments from Sections
  Create entries into SDWBlackboardSchedulerSISCourseSections
  Create entries into SDWBlackboardSchedulerSISCoursePersons
  Groups for PreExisting Courses??

## Slide 9: User/ENROLLMENT SYNC
User Sync
  Built into Application – Spring Task – Run at specific Times
  Uses BB Data Integration Framework – Snapshot Files
  Build Person File (Student and Staff)
  Build Staff Secondary Role File
  Need Logic for Institution Roles
Enrollment Sync
  Use Entries SDWBlackboardSchedulerSISCourseSections
  Use Entries SDWBlackboardSchedulerSISCoursePersons
  Added Group Fields
  Create Enrollment File to BB Data Integration Framework
  BB Data Integration does not support Groups.
  Recent Database Sync has lots of errors …. BB Courses Not in Staging
  Adding Group Sync – Just Push

## Slide 10: Issues
BB Scheduler
  How to handle Users in BB that are not in IC “joetest”
  Course Creation can take 20-30 seconds depending on data
  Group Data may need to be synced via REST API
  Need to limit BB Course List .. Will grow over time and needs to be managed

## Slide 11: Next STEPS
BB Scheduler
  Add Modify Sections
  Add Teacher and Students
  Discuss ”Manage Grades”
  Discuss “Admin” Role
BB Integration
  Add Enrollments to the Sync Process
  Complete User Sync Process
LTI API Implementation
  Test and verify on Windows Server
Windows Servers
  Test Login and Start Configuring
Continue UI Implementation
  Estimate 6 Weeks
Start Installation/Configuration Documents

## Slide 12: Wrap up
Estimate 10-14 Weeks To Implement
Any Concerns or Requests?
Questions/Answers